## Sprint 1
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
Verificação de Elegibilidade para Pedido de Ownership | https://github.com/see-paw/backend/issues/23 | ananasfofinho | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Criar apadrinhamento (Fostering) | https://github.com/see-paw/backend/issues/63 | joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/4
Criação e Validação de Pedido de Ownership | https://github.com/see-paw/backend/issues/25 | ananasfofinho | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Informação detalhada do animal | https://github.com/see-paw/backend/issues/53 | joelpinto-aw | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/3
Registo de Novos Animais no Sistema | https://github.com/see-paw/backend/issues/29 | cristianapinheiro98 | Done | HIGH | 3 | M (< 3 days) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/7
Mostrar listagem de animais disponíveis | https://github.com/see-paw/backend/issues/51 | cristianapinheiro98 | Done | HIGH | 1 | XS (< 1 hour) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/3
Listar e Consultar Animais do CAA | https://github.com/see-paw/backend/issues/36 | cristianapinheiro98 | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/7
Gestão do Ciclo de Vida de Pedidos de Ownership | https://github.com/see-paw/backend/issues/26 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Atualização do Estado do Animal após Aprovação de Ownership | https://github.com/see-paw/backend/issues/28 | Ruibaraujo | Done | HIGH | 1 | XS (< 1 hour) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6

## Sprint 2
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13
Title | Assignees | Status | Priority | Estimate | Size | Sprint | Start | date | End | date | Parent | issue

## Sprint 3
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
Agendar slot de visita/passeio | https://github.com/see-paw/backend/issues/78 | ananasfofinho | Done | HIGH | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Consultar disponibilidade de slots | https://github.com/see-paw/backend/issues/75 | joelpinto-aw | Done | HIGH | 4 | L (< 1 week) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Propor Período de Convivência (Ownership) | https://github.com/see-paw/backend/issues/34 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/10
Consulta e Acompanhamento de Pedidos de Ownership | https://github.com/see-paw/backend/issues/27 | Ruibaraujo | Done | HIGH | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/6
Cancelar slot agendado | https://github.com/see-paw/backend/issues/81 | Ruibaraujo | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Consultar Ownerships Ativos | https://github.com/see-paw/backend/issues/35 | ananasfofinho | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/6
Implementar a ordenação do catálogo de animais | https://github.com/see-paw/backend/issues/57 | cristianapinheiro98 | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/3
Implementar filtros de animais | https://github.com/see-paw/backend/issues/55 | joelpinto-aw | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/3
Cancelar apadrinhamento | https://github.com/see-paw/backend/issues/72 | cristianapinheiro98 | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Consultar lista de apadrinhamentos ativos | https://github.com/see-paw/backend/issues/69 | cristianapinheiro98 | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Página de perfil do CAA | https://github.com/see-paw/backend/issues/49 | cristianapinheiro98 | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2
Atualização de Dados de Animais Existentes | https://github.com/see-paw/backend/issues/30 | cristianapinheiro98 | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/7
Página de perfil do utilizador | https://github.com/see-paw/backend/issues/47 | cristianapinheiro98 | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2
Implementar registo de utilizador | https://github.com/see-paw/backend/issues/42 | ananasfofinho | Done | LOW | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2
Notificação de Decisão do Admin CAA ao utilizador | https://github.com/see-paw/backend/issues/38 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/8
Ver Lista de Favoritos | https://github.com/see-paw/backend/issues/22 | Ruibaraujo | Done | LOW | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/3
Remoção de Animais sem Vínculos Ativos | https://github.com/see-paw/backend/issues/31 | cristianapinheiro98 | Done | LOW | 1 | XS (< 1 hour) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/7
Implementar a autenticação do utilizador | https://github.com/see-paw/backend/issues/44 | joelpinto-aw | Done | LOW | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2

## Sprint 4
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
Implementar perfis de utilizador | https://github.com/see-paw/backend/issues/46 | joelpinto-aw | Done | LOW | 2 | S (< 1 day) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/2
Simulação de pagamento e recibo | https://github.com/see-paw/backend/issues/66 |  | Done | LOW | 3 | M (< 3 days) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/4
Notificação de Novo Agendamento ao Admin CAA | https://github.com/see-paw/backend/issues/40 | ananasfofinho | Done | LOW | 3 | M (< 3 days) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/8
Notificação de Novo Pedido de Ownership | https://github.com/see-paw/backend/issues/37 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/8
Simulação de Pagamento Mensal de Ownership | https://github.com/see-paw/backend/issues/33 |  | Done | LOW | 3 | M (< 3 days) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/6
Implementar pesquisa textual | https://github.com/see-paw/backend/issues/59 | joelpinto-aw | Done | LOW | 3 | M (< 3 days) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/3
Adicionar/Remover animais favoritos | https://github.com/see-paw/backend/issues/61 | cristianapinheiro98 | Done | LOW | 2 | S (< 1 day) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/3

## Backlog Backend
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
Agendar slot de visita/passeio | https://github.com/see-paw/backend/issues/78 | ananasfofinho | Done | HIGH | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Verificação de Elegibilidade para Pedido de Ownership | https://github.com/see-paw/backend/issues/23 | ananasfofinho | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Consultar disponibilidade de slots | https://github.com/see-paw/backend/issues/75 | joelpinto-aw | Done | HIGH | 4 | L (< 1 week) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Propor Período de Convivência (Ownership) | https://github.com/see-paw/backend/issues/34 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/10
Criar apadrinhamento (Fostering) | https://github.com/see-paw/backend/issues/63 | joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/4
Criação e Validação de Pedido de Ownership | https://github.com/see-paw/backend/issues/25 | ananasfofinho | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Informação detalhada do animal | https://github.com/see-paw/backend/issues/53 | joelpinto-aw | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/3
Registo de Novos Animais no Sistema | https://github.com/see-paw/backend/issues/29 | cristianapinheiro98 | Done | HIGH | 3 | M (< 3 days) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/7
Mostrar listagem de animais disponíveis | https://github.com/see-paw/backend/issues/51 | cristianapinheiro98 | Done | HIGH | 1 | XS (< 1 hour) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/3
Listar e Consultar Animais do CAA | https://github.com/see-paw/backend/issues/36 | cristianapinheiro98 | Done | HIGH | 2 | S (< 1 day) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/7
Gestão do Ciclo de Vida de Pedidos de Ownership | https://github.com/see-paw/backend/issues/26 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Atualização do Estado do Animal após Aprovação de Ownership | https://github.com/see-paw/backend/issues/28 | Ruibaraujo | Done | HIGH | 1 | XS (< 1 hour) | Sprint 1 (Retroativo) | 2025-10-11 | 2025-10-17 | https://github.com/see-paw/backend/issues/6
Consulta e Acompanhamento de Pedidos de Ownership | https://github.com/see-paw/backend/issues/27 | Ruibaraujo | Done | HIGH | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/6
Cancelar slot agendado | https://github.com/see-paw/backend/issues/81 | Ruibaraujo | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Consultar Ownerships Ativos | https://github.com/see-paw/backend/issues/35 | ananasfofinho | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/6
Implementar a ordenação do catálogo de animais | https://github.com/see-paw/backend/issues/57 | cristianapinheiro98 | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/3
Implementar filtros de animais | https://github.com/see-paw/backend/issues/55 | joelpinto-aw | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/3
Cancelar apadrinhamento | https://github.com/see-paw/backend/issues/72 | cristianapinheiro98 | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Consultar lista de apadrinhamentos ativos | https://github.com/see-paw/backend/issues/69 | cristianapinheiro98 | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/4
Página de perfil do CAA | https://github.com/see-paw/backend/issues/49 | cristianapinheiro98 | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2
Atualização de Dados de Animais Existentes | https://github.com/see-paw/backend/issues/30 | cristianapinheiro98 | Done | MEDIUM | 2 | S (< 1 day) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/7
Página de perfil do utilizador | https://github.com/see-paw/backend/issues/47 | cristianapinheiro98 | Done | MEDIUM | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2
Lembretes de Levantamento/Entrega | https://github.com/see-paw/backend/issues/39 | ananasfofinho | Done | LOW | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/8
Implementar registo de utilizador | https://github.com/see-paw/backend/issues/42 | ananasfofinho | Done | LOW | 3 | M (< 3 days) | Sprint 3 | 2025-10-25 | 2025-10-30 | https://github.com/see-paw/backend/issues/2
Implementar perfis de utilizador | https://github.com/see-paw/backend/issues/46 | joelpinto-aw | Done | LOW | 2 | S (< 1 day) | Sprint 4 | 2025-11-01 | 2025-11-07 | https://github.com/see-paw/backend/issues/2