## WebApp
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
WA: Agendar Convivência | https://github.com/see-paw/web-app/issues/8 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/10
WA: Pedido de Ownership | https://github.com/see-paw/web-app/issues/26 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/6
WA: Formulário e Registo do Pedido de Ownership | https://github.com/see-paw/web-app/issues/28 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/6
WA: Visualização do Estado do Pedido de Ownership (Utilizador) | https://github.com/see-paw/web-app/issues/30 |  | Backlog | HIGH | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/6
WA: Consultar a disponibilidade de slots | https://github.com/see-paw/web-app/issues/38 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/4
WA: Agendar slot de visita/passeio | https://github.com/see-paw/web-app/issues/39 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/4
WA: Criar página de perfil do utilizador | https://github.com/see-paw/web-app/issues/17 |  | Backlog | MEDIUM | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/2
WA: Criar página de perfil do CAA | https://github.com/see-paw/web-app/issues/18 |  | Backlog | MEDIUM | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/2
WA: Visualização dos termos do processo Ownership | https://github.com/see-paw/web-app/issues/27 |  | Backlog | MEDIUM | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/6
WA: Editar Informações de Animal | https://github.com/see-paw/web-app/issues/32 |  | Backlog | MEDIUM | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/7
WA: Remoção de Animal do CAA | https://github.com/see-paw/web-app/issues/33 |  | Backlog | MEDIUM | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/7
WA: Implementar registo de utilizador com email e palavra-passe | https://github.com/see-paw/web-app/issues/15 |  | Backlog | LOW | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/2
WA: Implementar ordenação do catálogo de animais | https://github.com/see-paw/web-app/issues/22 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/3
WA: Implementar pesquisa textual | https://github.com/see-paw/web-app/issues/23 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/3
WA: Implementar funcionalidade de animais favoritos | https://github.com/see-paw/web-app/issues/25 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/3
WA: Página de Favoritos | https://github.com/see-paw/web-app/issues/6 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/3
WA: Página de Ownerships Ativos | https://github.com/see-paw/web-app/issues/9 |  | Backlog | LOW | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/6
WA: Notificação de Agendamento | https://github.com/see-paw/web-app/issues/14 |  | Backlog | LOW | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/8
WA: Consultar lista de apadrinhamentos ativos | https://github.com/see-paw/web-app/issues/36 |  | Backlog | LOW | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/4
WA: Cancelar apadrinhamento | https://github.com/see-paw/web-app/issues/37 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/4
WA: Cancelar slot agendado | https://github.com/see-paw/web-app/issues/40 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/4
WA: Aprovação pelo CAA do Pedido de Ownership | https://github.com/see-paw/web-app/issues/29 | Ruibaraujo | Done | HIGH | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/6
WA: Criar apadrinhamento (fostering) | https://github.com/see-paw/web-app/issues/34 | cristianapinheiro98 | Done | HIGH | 4 | L (< 1 week) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/4
WA: Implementar listagem de animais disponíveis | https://github.com/see-paw/web-app/issues/19 | ananasfofinho, joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/3
WA: Página de Gestão de Animais | https://github.com/see-paw/web-app/issues/10 | ananasfofinho, joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/7
WA: Adicionar Animal | https://github.com/see-paw/web-app/issues/31 | ananasfofinho | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/7
WA: Criar página detalhada do animal | https://github.com/see-paw/web-app/issues/20 | ananasfofinho, joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/3
WA: Exibir Lembretes/Notificações de levantamento/entrega | https://github.com/see-paw/web-app/issues/13 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/8
WA: Notificação de Novo Pedido de Ownership (Admin CAA) | https://github.com/see-paw/web-app/issues/11 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/8
WA: Notificação de Decisão do Admin CAA ao utilizador | https://github.com/see-paw/web-app/issues/12 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/8
WA: Pagamento e Recibo de Ownership | https://github.com/see-paw/web-app/issues/7 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/6
WA: Simulação de pagamento e recibo | https://github.com/see-paw/web-app/issues/35 | cristianapinheiro98 | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/4
WA: Implementar filtros de animais | https://github.com/see-paw/web-app/issues/21 | ananasfofinho | Done | LOW | 3 | L (< 1 week) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/3
WA: Implementar autenticação com email e palavra-passe | https://github.com/see-paw/web-app/issues/16 | joelpinto-aw | Done | LOW | 2 | S (< 1 day) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/2

## WebApp-Sprint5
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
WA: Implementar listagem de animais disponíveis | https://github.com/see-paw/web-app/issues/19 | ananasfofinho, joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/3
WA: Página de Gestão de Animais | https://github.com/see-paw/web-app/issues/10 | ananasfofinho, joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/7
WA: Adicionar Animal | https://github.com/see-paw/web-app/issues/31 | ananasfofinho | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/7
WA: Criar página detalhada do animal | https://github.com/see-paw/web-app/issues/20 | ananasfofinho, joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/3
WA: Implementar filtros de animais | https://github.com/see-paw/web-app/issues/21 | ananasfofinho | Done | LOW | 3 | L (< 1 week) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/3
WA: Implementar autenticação com email e palavra-passe | https://github.com/see-paw/web-app/issues/16 | joelpinto-aw | Done | LOW | 2 | S (< 1 day) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/2

## WebApp-Sprint8
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
WA: Aprovação pelo CAA do Pedido de Ownership | https://github.com/see-paw/web-app/issues/29 | Ruibaraujo | Done | HIGH | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/6
WA: Criar apadrinhamento (fostering) | https://github.com/see-paw/web-app/issues/34 | cristianapinheiro98 | Done | HIGH | 4 | L (< 1 week) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/4
WA: Exibir Lembretes/Notificações de levantamento/entrega | https://github.com/see-paw/web-app/issues/13 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/8
WA: Notificação de Novo Pedido de Ownership (Admin CAA) | https://github.com/see-paw/web-app/issues/11 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/8
WA: Notificação de Decisão do Admin CAA ao utilizador | https://github.com/see-paw/web-app/issues/12 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/8
WA: Pagamento e Recibo de Ownership | https://github.com/see-paw/web-app/issues/7 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/6
WA: Simulação de pagamento e recibo | https://github.com/see-paw/web-app/issues/35 | cristianapinheiro98 | Done | LOW | 3 | M (< 3 days) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/4

## AndroidApp
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
AP: Consultar a disponibilidade de slots | https://github.com/see-paw/android-app/issues/37 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/4
AP: Agendar slot de visita/passeio | https://github.com/see-paw/android-app/issues/38 |  | Backlog | HIGH | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/4
AP: Criar página de perfil do utilizador | https://github.com/see-paw/android-app/issues/39 |  | Backlog | MEDIUM | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/2
AP: Cancelar slot agendado | https://github.com/see-paw/android-app/issues/53 |  | Backlog | LOW | 2 | S (< 1 day) |  |  |  | https://github.com/see-paw/backend/issues/4
AP: Simulação de pagamento e recibo | https://github.com/see-paw/android-app/issues/51 |  | Backlog | LOW | 3 | M (< 3 days) |  |  |  | https://github.com/see-paw/backend/issues/4
AP: Criar apadrinhamento (fostering) | https://github.com/see-paw/android-app/issues/34 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/4
AP: Agendar Convivência | https://github.com/see-paw/android-app/issues/33 | joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 8 | 2025-12-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/10
AP: Criar página detalhada do animal | https://github.com/see-paw/android-app/issues/30 | cristianapinheiro98 | Done | HIGH | 2 | S (< 1 day) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/3
AP: Formulário e Registo do Pedido de Ownership | https://github.com/see-paw/android-app/issues/35 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Pedido de Ownership | https://github.com/see-paw/android-app/issues/31 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/6
AP: Implementar listagem de animais disponíveis | https://github.com/see-paw/android-app/issues/55 | cristianapinheiro98 | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/3
AP: Consultar lista de apadrinhamentos ativos | https://github.com/see-paw/android-app/issues/43 | Ruibaraujo | Done | MEDIUM | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/4
AP: Ecrã de Favoritos | https://github.com/see-paw/android-app/issues/32 | ananasfofinho | Done | MEDIUM | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/3
AP: Implementar funcionalidade de animais favoritos | https://github.com/see-paw/android-app/issues/40 | ananasfofinho | Done | MEDIUM | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/3
AP: Visualização do Estado do Pedido de Ownership | https://github.com/see-paw/android-app/issues/41 | Ruibaraujo | Done | MEDIUM | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Lista de Ownerships Ativos | https://github.com/see-paw/android-app/issues/36 | Ruibaraujo | Done | MEDIUM | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Visualização dos termos do processo Ownership | https://github.com/see-paw/android-app/issues/42 | Ruibaraujo | Done | MEDIUM | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Cancelar apadrinhamento | https://github.com/see-paw/android-app/issues/52 | Ruibaraujo | Done | LOW | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/4
AP: Implementar autenticação com email e palavra-passe | https://github.com/see-paw/android-app/issues/48 | Ruibaraujo | Done | LOW | 2 | S (< 1 day) | Sprint 6 | 2025-11-15 | 2025-11-21 | https://github.com/see-paw/backend/issues/2
AP: Implementar pesquisa textual | https://github.com/see-paw/android-app/issues/50 | cristianapinheiro98 | Done | LOW | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/3
AP: Implementar registo de utilizador com email e palavra-passe | https://github.com/see-paw/android-app/issues/47 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 6 | 2025-12-15 | 2025-11-21 | https://github.com/see-paw/backend/issues/2
AP: Implementar filtros de animais | https://github.com/see-paw/android-app/issues/49 | cristianapinheiro98 | Done | LOW | 3 | M (< 3 days) | Sprint 6 | 2025-11-15 | 2025-11-21 | https://github.com/see-paw/backend/issues/3
AP: Implementar ordenação da listagem de animais | https://github.com/see-paw/android-app/issues/54 | cristianapinheiro98 | Done | LOW | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/3
AP: Pagamento e Recibo de Ownership | https://github.com/see-paw/android-app/issues/44 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Notificação de Decisão do Admin CAA ao utilizador | https://github.com/see-paw/android-app/issues/45 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/8
AP: Exibir Lembretes/Notificações de levantamento/entrega | https://github.com/see-paw/android-app/issues/46 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-12-28 | https://github.com/see-paw/backend/issues/8

## AndroidApp-Sprint5
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
AP: Criar página detalhada do animal | https://github.com/see-paw/android-app/issues/30 | cristianapinheiro98 | Done | HIGH | 2 | S (< 1 day) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/3
AP: Pedido de Ownership | https://github.com/see-paw/android-app/issues/31 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-11-14 | https://github.com/see-paw/backend/issues/6
AP: Implementar listagem de animais disponíveis | https://github.com/see-paw/android-app/issues/55 | cristianapinheiro98 | Done | HIGH | 3 | M (< 3 days) | Sprint 5 | 2025-11-08 | 2025-12-14 | https://github.com/see-paw/backend/issues/3

## AndroidApp-Sprint6
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
AP: Implementar autenticação com email e palavra-passe | https://github.com/see-paw/android-app/issues/48 | Ruibaraujo | Done | LOW | 2 | S (< 1 day) | Sprint 6 | 2025-11-15 | 2025-11-21 | https://github.com/see-paw/backend/issues/2
AP: Implementar registo de utilizador com email e palavra-passe | https://github.com/see-paw/android-app/issues/47 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 6 | 2025-12-15 | 2025-11-21 | https://github.com/see-paw/backend/issues/2
AP: Implementar filtros de animais | https://github.com/see-paw/android-app/issues/49 | cristianapinheiro98 | Done | LOW | 3 | M (< 3 days) | Sprint 6 | 2025-11-15 | 2025-11-21 | https://github.com/see-paw/backend/issues/3

## AndroidApp-Sprint7
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
AP: Criar apadrinhamento (fostering) | https://github.com/see-paw/android-app/issues/34 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/4
AP: Formulário e Registo do Pedido de Ownership | https://github.com/see-paw/android-app/issues/35 | Ruibaraujo | Done | HIGH | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Consultar lista de apadrinhamentos ativos | https://github.com/see-paw/android-app/issues/43 | Ruibaraujo | Done | MEDIUM | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/4
AP: Visualização do Estado do Pedido de Ownership | https://github.com/see-paw/android-app/issues/41 | Ruibaraujo | Done | MEDIUM | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Lista de Ownerships Ativos | https://github.com/see-paw/android-app/issues/36 | Ruibaraujo | Done | MEDIUM | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Visualização dos termos do processo Ownership | https://github.com/see-paw/android-app/issues/42 | Ruibaraujo | Done | MEDIUM | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Implementar pesquisa textual | https://github.com/see-paw/android-app/issues/50 | cristianapinheiro98 | Done | LOW | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/3
AP: Implementar ordenação da listagem de animais | https://github.com/see-paw/android-app/issues/54 | cristianapinheiro98 | Done | LOW | 2 | S (< 1 day) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/3
AP: Pagamento e Recibo de Ownership | https://github.com/see-paw/android-app/issues/44 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/6
AP: Notificação de Decisão do Admin CAA ao utilizador | https://github.com/see-paw/android-app/issues/45 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-11-28 | https://github.com/see-paw/backend/issues/8
AP: Exibir Lembretes/Notificações de levantamento/entrega | https://github.com/see-paw/android-app/issues/46 | Ruibaraujo | Done | LOW | 3 | M (< 3 days) | Sprint 7 | 2025-11-22 | 2025-12-28 | https://github.com/see-paw/backend/issues/8

## AndroidApp-Sprint8
Title | URL | Assignees | Status | Priority | Estimate | Size | Sprint | Start date | End date | Parent issue
AP: Agendar Convivência | https://github.com/see-paw/android-app/issues/33 | joelpinto-aw | Done | HIGH | 3 | M (< 3 days) | Sprint 8 | 2025-12-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/10
AP: Ecrã de Favoritos | https://github.com/see-paw/android-app/issues/32 | ananasfofinho | Done | MEDIUM | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/3
AP: Implementar funcionalidade de animais favoritos | https://github.com/see-paw/android-app/issues/40 | ananasfofinho | Done | MEDIUM | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/3
AP: Cancelar apadrinhamento | https://github.com/see-paw/android-app/issues/52 | Ruibaraujo | Done | LOW | 2 | S (< 1 day) | Sprint 8 | 2025-11-29 | 2025-12-05 | https://github.com/see-paw/backend/issues/4